## SPATIUM CPA-TRADITIONAL
SPATIUM: CRITICAL PATH ANALYSIS: TRADITIONAL
0 | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 7 |  | 7 | 3 | 10 |  |  |  | 11 | 3 | 14
1.1 scheme design |  |  | 1.2 detailed design |  |  | 1.3 drawings & specs |  |  |  | 2.1 demolition & excvn | [5 empty] | 2.4 lower seating
0 |  | 2 | 2 |  | 5 | 5 |  | 7 |  | 7 |  | 10 |  | (+1) |  | 20 |  | 23
[9 empty] | (+1) |  | 8 | 2 | 10 |  | 10 | 4 | 14
[11 empty] | 2.2 substructures |  |  |  | 2.3 lower superstruct's
[11 empty] | 8 |  | 10 |  | 10 |  | 14
[23 empty] | 19 | 3 | 22
3.4 finishes & fitting out
[19 empty] | 14 | 5 | 19 |  | 20 |  | 23
3.1 upper superstruct's
[19 empty] | 14 |  | 19 |  | 19 | 4 | 23
Early Start |  | DURATION | Early Finish | [15 empty] | (+1) |  |  |  | 3.5 external works
TASK | [19 empty] | 15 | 3 | 18 | 19 |  | 23
Late Start |  | FLOAT | Late Finish | [16 empty] | 3.2 cladding
[18 empty] | (+1) |  | 18 |  | 21 |  | 20 | 2 | 22 | 23 | 1 | 24
N.B. start and finish dates are always “end of” a month | [23 empty] | 3.6 special installations |  |  | 3.7 commissioning
[20 empty] | 15 | 5 | 20 |  | 21 |  | 23 | 23 |  | 24
REFERRING TO PAGES 10 & 11 IN THE PROJECT BRIEF (AND FOR BOTH PROCUREMENT STRATEGIES): | [19 empty] | 3.3 M & E services
[20 empty] | 16 |  | 21
STEP 1: VERIFY THE LOGICAL FLOW, AND THEN DO THE “FORWARD PASS”:
INDICATE THE EARLY START AND EARLY FINISH TIMES FOR EACH TASK
(ALREADY DONE FOR 1.1)
STEP 2: DO THE “BACKWARD PASS”:
THE LATE FINISH IS THE LATEST A TASK CAN FINISH WITHOUT CHANGING THE END DATE OF THE PROJECT:
LATE FINISH – DURATION = LATE START
LATE START – EARLY START = FLOAT

## SPATIUM CPA-DESIGN&BUILD
SPATIUM: CRITICAL PATH ANALYSIS: DESIGN & BUILD
0 | 2 | 2 | 2 | 3 | 5 | 5 | 2 | 7 |  | 7 | 2 | 9 |  |  | 10 | 3 | 13
1.1 scheme design |  |  | 1.2 detailed design |  |  | 1.3 drawings & specs |  |  |  | 2.2 substructures |  |  |  |  | 2.4 lower seating
[5 empty] | 1 | 2 |  | 4 |  | 4 |  | 6 | (+1) |  | 19 |  | 22
(+1)
[7 empty] | 5 | 3 | 8 |  |  |  |  | 9 | 4 | 13
[7 empty] | 2.1 demolition & excvn | [6 empty] | 2.3 lower superstruct's
[7 empty] | 1 |  | 4 |  |  |  |  | 6 |  | 10
[22 empty] | 18 | 3 | 21
3.4 finishes & fitting out
[18 empty] | 13 | 5 | 18 |  | 19 |  | 22
3.1 upper superstruct's
[18 empty] | 10 |  | 15 |  | 18 | 4 | 22
Early Start |  | DURATION | Early Finish | [14 empty] | (+1) |  |  |  | 3.5 external works
TASK | [18 empty] | 14 | 3 | 17 | 18 |  | 22
Late Start |  | FLOAT | Late Finish | [15 empty] | 3.2 cladding
[17 empty] | (+1) |  | 17 |  | 20 |  | 19 | 2 | 21 | 22 | 1 | 23
N.B. start and finish dates are always “end of” a month | [22 empty] | 3.6 special installations |  |  | 3.7 commissioning
[19 empty] | 14 | 5 | 19 |  | 20 |  | 22 | 22 |  | 23
REFERRING TO PAGES 10 & 11 IN THE PROJECT BRIEF (AND FOR BOTH PROCUREMENT STRATEGIES): | [18 empty] | 3.3 M & E services
[19 empty] | 15 |  | 20
STEP 1: VERIFY THE LOGICAL FLOW, AND THEN DO THE “FORWARD PASS”:
INDICATE THE EARLY START AND EARLY FINISH TIMES FOR EACH TASK
(ALREADY DONE FOR 1.1)
STEP 2: DO THE “BACKWARD PASS”:
THE LATE FINISH IS THE LATEST A TASK CAN FINISH WITHOUT CHANGING THE END DATE OF THE PROJECT:
LATE FINISH – DURATION = LATE START
LATE START – EARLY START = FLOAT

## Traditional-Table
Task | Duration | Dependency
1.1 | 2
1.2 | 3 | 1.1
1.3 | 2 | 1.2
2.1 | 3 | 1.3
2.2 | 2 | 2.1(S +1)
2.3 | 4 | 2.1, 2.2
2.4 | 3 | 2.3(S +1)
3.1 | 5 | 2.3
3.2 | 3 | 3.1(S +1)
3.3 | 5 | 3.1(S +1)
3.4 | 3 | 3.1
3.5 | 4 | 3.1
3.6 | 2 | 3.2, 3.3
3.7 | 1 | 2.4, 3.4, 3.5, 3.6

## D&B-Table
Task | Duration | Dependency
1.1 | 2
1.2 | 3 | 1.1
1.3 | 2 | 1.2
2.1 | 3 | 1.2
2.2 | 2 | 1.3
2.3 | 4 | 2.1, 2.2
2.4 | 3 | 2.3(S +1)
3.1 | 5 | 2.3
3.2 | 3 | 3.1(S +1)
3.3 | 5 | 3.1(S +1)
3.4 | 3 | 3.1
3.5 | 4 | 3.1
3.6 | 2 | 3.2, 3.3
3.7 | 1 | 2.4, 3.4, 3.5, 3.6